OA Presence at Council Events Sequoyah Lodge · Planning Guide for Lodge Officers & Lodge Adviser

This guide helps your lodge plan a visible, meaningful OA presence at council-level events: Scout Fairs, Council Camporees, Eagle Scout Recognition Dinners, University of Scouting, and council fundraisers. Council events are bigger stages than district roundtables — they require more planning, more volunteers, and a higher degree of coordination with council professional staff.

1  WHY COUNCIL EVENTS ARE DIFFERENT

District events are chapter-level work: one chapter chief, a small table, a few conversations. Council events operate at a completely different scale and carry different expectations:

| District Events | Council Events |
| --- | --- |
| 1–2 lodge members staff a table | 5–10+ members needed across shifts and stations |
| Chapter chief coordinates independently | Lodge Chief or VP coordinates with council staff |
| Audience: unit leaders from one district | Audience: families, Scouts, and leaders from across the entire council |
| Informal setup — a table and some flyers | Formal booth, display, or program slot; may require pre-registration |
| Follow-up with a few Scoutmasters | Follow-up with council Key 3, Scout Executive, and multiple district contacts |

The payoff is proportional: a strong OA showing at a council event puts the lodge in front of hundreds of families and positions the Order of the Arrow as a visible, valued partner to the council — not a program that exists only on induction weekends.

2  BUILDING THE COUNCIL RELATIONSHIP

Before you can show up at council events, you need a working relationship with the people who plan them. This is primarily the Lodge Adviser’s and Lodge Chief’s responsibility.

Council Key 3 & Staff Contacts

| Role | Name | Phone / Email |
| --- | --- | --- |
| Scout Executive / CEO | NAME | PHONE / EMAIL |
| Council President | NAME | PHONE / EMAIL |
| Council Commissioner | NAME | PHONE / EMAIL |
| Program Director | NAME | PHONE / EMAIL |
| Camping / Activities Director | NAME | PHONE / EMAIL |
| Council Advancement Chair | NAME | PHONE / EMAIL |
| OA Staff Adviser | NAME | PHONE / EMAIL |

Relationship-building actions:

- Lodge Adviser should attend at least one council board or committee meeting per year to stay visible to council leadership.

- Lodge Chief should introduce themselves to the Scout Executive at the start of each program year and ask: “What council events could the OA support this year?”

- Offer the lodge as a service resource — council events always need extra hands, and volunteering builds goodwill before you ever ask for booth space.

- Send a brief year-end summary of OA activities and service hours to the Scout Executive. Visibility with council leadership is earned through communication.

3  COUNCIL EVENT PLANNING TIMELINE

Council events require longer lead times than district events. Start planning 8–10 weeks out.

8–10 WEEKS BEFORE

Confirm event date, location, and format with the council program director or event chair.

Determine the lodge’s role: information booth, ceremony, service support, activity station, or program presentation.

Submit any required registration, booth requests, or program proposals to the council.

Assign an Event Lead (lodge officer) who will own all coordination for this event.

Draft a volunteer roster — target 5–10 members depending on event scale.

4–6 WEEKS BEFORE

Confirm booth/space assignment and any special requirements (electricity, tent, vehicle access).

Design and order any event-specific materials: banners, flyers, handouts, QR code signs.

Coordinate with council staff on schedule placement — know exactly when the OA is on the program.

Finalize volunteer roster with confirmed names, shift assignments, and transportation plan.

Brief all volunteers on messaging using the Talking Points Guide (T2).

1 WEEK BEFORE

Final confirmation with all volunteers: who, when, where, what to wear.

Pack the council event kit (see Section 4 — larger than the district table kit).

Prepare any ceremony materials if a call-out or crossover is planned.

Print fresh copies of the sign-up sheet, event flyers, and QR code cards.

Send a reminder to the council contact confirming the lodge’s participation.

4  COUNCIL EVENT KIT — WHAT TO BRING

Council events justify a more polished setup than a district roundtable table. Think “booth” rather than “table.”

| Item | Notes |
| --- | --- |
| Lodge display banner (freestanding) | A pull-up banner or PVC frame banner that can stand behind the booth. Far more visible than a table sign. |
| OA tablecloth (branded) | Clean, wrinkle-free, in OA colors. First impression matters at council scale. |
| OA brochures & flyers | Lodge-branded with current program year dates. Print 50–100+ for council events. |
| Current events rack card | Postcard-sized handout with the next 3–4 lodge events. Easy for families to pocket. |
| Unit election sign-up sheet | Columns: Troop #, Scoutmaster name, phone, email. Target 10+ contacts per council event. |
| QR code display (laminated) | Link to lodge website, LodgeMaster registration, or social media. Make it large — at least 5×5 inches. |
| Lodge patches / giveaways | Trading patches, stickers, or small items for Scouts visiting the booth. Draws foot traffic. |
| Photo display or slideshow | Tablet or printed photos showing lodge events in action. Real photos > any brochure. |
| Talking Points Guide (T2) | Enough copies for every volunteer staffing the booth. |
| Volunteer schedule printout | Posted at the booth so everyone knows their shift. |

5  AT THE EVENT — WORKING A COUNCIL-SCALE PRESENCE

| 1 | Set up early and stay late. Council events have long windows. Be ready before the first family walks in and don’t tear down while attendees are still around. |
| --- | --- |
| 2 | Staff in shifts of 2–3. Nobody should work the booth alone, and nobody should be stuck there all day. Rotate every 60–90 minutes. |
| 3 | Dress the part. OA sash, lodge t-shirt, or field uniform. At council scale, you’re representing the lodge to people who may never have seen the OA in person. |
| 4 | Engage Scouts AND parents. At council events, parents are often the decision-makers. Be ready to explain OA membership, the election process, and what their Scout gains from participation. |
| 5 | Connect with council leadership in person. If the Scout Executive, Council President, or Program Director is at the event, introduce yourself and thank them for the opportunity. A 30-second conversation builds more goodwill than any email. |
| 6 | Collect contacts aggressively. Your goal at a council event is 10+ new unit leader contacts. Every conversation about elections should end with a name on your sign-up sheet. |
| 7 | Document everything. Take photos of the booth, volunteers, and interactions. These become social media content and evidence for your year-end council report. |

6  AFTER THE EVENT — FOLLOW-UP WITHIN ONE WEEK

Send a thank-you email to the council event chair and any council staff who helped coordinate your participation.

Send follow-up emails to all unit leaders who signed the contact sheet. Use Template T4 (Post-Event Thank-You).

Add new contacts to the lodge’s master contacts list in Google Drive.

Post event photos and a brief recap to lodge social media channels within 48 hours.

Report attendance, contacts collected, and volunteer hours to the Lodge Secretary.

Schedule election visits for any units who expressed interest.

Restock the council event kit: note materials that need reprinting, repair, or replacement.

Complete the event debrief below with your volunteer team.

Event Debrief Notes:

| Question | Notes |
| --- | --- |
| What worked well? |  |
| What should we change next time? |  |
| How many contacts collected? |  |
| Any follow-up commitments made? |  |
| Council staff feedback (if any)? |  |

7  TARGET COUNCIL EVENTS — UPDATE EACH PROGRAM YEAR

Identify specific council events and assign a lodge officer or event lead at the start of each program year. Aim for OA presence at a minimum of 4 council events annually.

| Event | Date | Event Lead | Volunteers Needed | Status |
| --- | --- | --- | --- | --- |
| Council Scout Fair / Expo | MM/DD/YYYY | NAME | # | STATUS |
| Council Camporee | MM/DD/YYYY | NAME | # | STATUS |
| Eagle Scout Recognition Dinner | MM/DD/YYYY | NAME | # | STATUS |
| University of Scouting | MM/DD/YYYY | NAME | # | STATUS |
| Council Annual Business Meeting | MM/DD/YYYY | NAME | # | STATUS |
| Council Fundraiser / Auction | MM/DD/YYYY | NAME | # | STATUS |
| Day Camp Closing Ceremonies | MM/DD/YYYY | NAME | # | STATUS |
| Council Volunteer Appreciation | MM/DD/YYYY | NAME | # | STATUS |

TIP: Council events are the lodge’s highest-visibility opportunities. A polished, well-staffed OA booth at a Scout Fair does more for lodge recruitment than months of roundtable reports. Invest the planning time — it pays off.