## How to Use
How to Use This Checklist
Step 1 — Enter Event Info | Go to "Event Planning Checklist" tab. Fill in Event Name, Event Date (T), and Event Chair in row 3.
Step 2 — Calculate Dates | In the Due Date column (E), enter the actual calendar date for each milestone. Use your event date minus the number of weeks shown in column B.
Step 3 — Assign Owners | Review the default Owner column and update to reflect your actual planning team roles. Owners must be named individuals, not just role titles.
Step 4 — Track Progress | Update Status each week at your planning meetings. Use: Not Started → In Progress → Complete (or Blocked / N/A).
Step 5 — Add Notes | Use the Notes column to link Google Drive docs, record vendor contacts, note issues, or flag dependencies.
Phase Color Guide | CONCEPT (green) ¦ DESIGN (blue) ¦ BUILD (orange) ¦ PROMOTE (purple) ¦ EXECUTE (dark green) ¦ WRAP-UP (gray)
Customizing | Add rows for event-specific tasks by inserting rows within the correct phase block. Do not delete phase label rows.
After the Event | Complete the WRAP-UP phase tasks within T+2 weeks. Then archive this file in your event's Google Drive folder and hand to incoming chair.

## Event Planning Checklist
Sequoyah Lodge — Event Planning Master Checklist & Timeline
Backwards-mapped from Event Date (T) · Update weekly · Hand off to incoming chair after post-event wrap
Event Name: |  | Event Date (T): |  | Event Chair:
Phase | Weeks Out | Task / Milestone | Owner | Due Date | Status | Notes / Links
CONCEPT
CONCEPT | T-16 | LEC reviews and approves event concept (T19 form submitted) | Event Chair Candidate |  | Not Started
CONCEPT | T-16 | Event Chair officially assigned by Lodge Chief | Lodge Chief |  | Not Started | Announce at LEC meeting
CONCEPT | T-15 | Chair assembles core planning team (min. 3 youth) | Event Chair |  | Not Started
CONCEPT
CONCEPT | T-14 | Kickoff planning meeting held; roles assigned | Event Chair |  | Not Started
CONCEPT | T-14 | Venue research begins (3 options identified) | Logistics Lead |  | Not Started
CONCEPT | T-13 | Initial budget drafted and submitted to Lodge Adviser | Treasurer / Chair |  | Not Started | Use T21 Budget Template
DESIGN
DESIGN | T-12 | Venue confirmed and deposit paid (if required) | Logistics Lead |  | Not Started | Get confirmation in writing
DESIGN | T-12 | LodgeMaster event listing updated with confirmed details | LodgeMaster Admin |  | Not Started
DESIGN | T-12 | Patch/apparel design brief submitted (if custom merch) | Creativity Officer |  | Not Started | Use T14 Design Brief Template
DESIGN | T-11 | Registration form drafted and tested in LodgeMaster | LodgeMaster Admin |  | Not Started | Test with 2-3 internal users
DESIGN | T-11 | Event program/agenda outline drafted | Event Chair |  | Not Started
DESIGN | T-11 | Ceremony team identified and script assigned (if applicable) | Ceremony Chief |  | Not Started
DESIGN
DESIGN | T-10 | Patch art approved by Lodge Chief / Adviser | Lodge Chief |  | Not Started | Approve via T16 Rubric
DESIGN | T-9 | Staffing plan drafted (all roles, youth vs. adult) | Event Chair |  | Not Started
DESIGN | T-9 | Transportation/carpool coordination plan outlined | Logistics Lead |  | Not Started
BUILD
BUILD | T-8 | Registration opens in LodgeMaster | LodgeMaster Admin |  | Not Started | Confirm link works before promoting
BUILD | T-8 | Communications calendar updated (T10) with event promotions | Communications Officer |  | Not Started | Min. 3 touchpoints planned
BUILD | T-8 | First event announcement sent to full lodge (email + social) | Communications Officer |  | Not Started | Use T12 / social calendar
BUILD | T-7 | All vendor orders placed (food, supplies, A/V) | Logistics Lead |  | Not Started
BUILD | T-6 | Patch/apparel order placed with vendor | Creativity Officer |  | Not Started | Confirm lead time with vendor
BUILD
BUILD | T-5 | All staff roles confirmed and communicated | Event Chair |  | Not Started | Send staff packet
BUILD | T-5 | Run-of-show (T22) drafted and shared with core team | Event Chair |  | Not Started
BUILD | T-5 | Trading post inventory planned (if applicable) | Treasurer |  | Not Started
PROMOTE
PROMOTE | T-4 | Second reminder sent (email + social) | Communications Officer |  | Not Started | Highlight registration deadline
PROMOTE | T-4 | Registration deadline set / early-bird closes | LodgeMaster Admin |  | Not Started
PROMOTE | T-3 | Final headcount from LodgeMaster pulled for planning | Event Chair |  | Not Started | Share with food/logistics leads
PROMOTE | T-3 | Final staffing confirmed (no gaps) | Event Chair |  | Not Started
PROMOTE
PROMOTE | T-2 | Run-of-show finalized and distributed to ALL staff | Event Chair |  | Not Started | Use T22 template
PROMOTE | T-2 | Final supplies checklist completed | Logistics Lead |  | Not Started
PROMOTE | T-2 | Patch/apparel confirmed received and counted | Creativity Officer |  | Not Started
EXECUTE
EXECUTE | T-1 | Staff briefing / walk-through call held | Event Chair |  | Not Started | 30-min call or in-person
EXECUTE | T-1 | Emergency contacts list distributed to all staff | Lodge Adviser |  | Not Started
EXECUTE | T-1 | Site setup assignments confirmed | Logistics Lead |  | Not Started
EXECUTE | T-0 | Site setup completed per run-of-show | All Staff |  | Not Started | Arrive 2 hrs early minimum
EXECUTE | T-0 | Registration/check-in table staffed and ready | Registration Lead |  | Not Started
EXECUTE
EXECUTE | T-0 | Event executed per run-of-show | All Staff |  | Not Started
EXECUTE | T-0 | Attendance count taken (opening + closing) | Event Chair |  | Not Started | Record in notes
EXECUTE | T-0 | Trading post / merchandise sales recorded | Treasurer |  | Not Started
WRAP-UP
WRAP-UP | T+1 | Venue cleaned and returned to original condition | Logistics Lead |  | Not Started | Get venue sign-off if required
WRAP-UP | T+1 | All income/expenses recorded in budget actuals (T21) | Treasurer |  | Not Started
WRAP-UP | T+1 | Photos/assets uploaded to Digital Asset Library (T17) | Communications Officer |  | Not Started